## Slide 1: Ecosystem-based Adaptation in the Indian Ocean
July 21, 2021
Inception workshop
© Cristina Mittermeier

## Slide 2
• Ensure a common understanding among AFD, the CEPF Secretariat, NDAs and other stakeholders on the rationale, theory of change and expected results of the program.
• Consider relevant policies and requirements of AFD and the GCF and their implications for CEPF’s established policies and procedures.
• Review the annual workplan for Fiscal Year 2022.
• Identify opportunities for collaboration and alignment with other active and pipeline projects of AFD, GCF and the governments of the four program countries, especially ones that focus on climate adaptation.
© Conservation International/photo by Rachel Neugarten
OBJECTIVES
Notes: CEPF brings people and organizations together to protect some of Earth’s most biologically diverse yet threatened ecosystems.
Six global donors make this work possible: The French Development Agency, Conservation International, the European Union, the Global Environment Facility, the Government of Japan and the World Bank.

## Slide 3
CEPF is a joint initiative of:
l'Agence Française de Développement
Conservation International
The European Union
The Global Environment Facility
The Government of Japan
The World Bank
© Robin Moore/iLCP
PARTNERSHIP
Notes: CEPF brings people and organizations together to protect some of Earth’s most biologically diverse yet threatened ecosystems.
Six global donors make this work possible: The French Development Agency, Conservation International, the European Union, the Global Environment Facility, the Government of Japan and the World Bank.

## Slide 5: Biodiversity Hotspots
Current CEPF investment
Past CEPF investment
Eligible for CEPF investment
Other hotspots
Atlantic Forest
Caribbean Islands
Cape Floristic Region
Caucasus
Cerrado
Chilean Winter Rainfall–Valdivian Forests
Coastal Forests of Eastern Africa
East Melanesian Islands
Eastern Afromontane
Forests of East Australia
Guinean Forests of West Africa
Himalaya
Horn of Africa
Indo-Burma
Irano-Anatolian
Japan
Madagascar and the Indian Ocean Islands
Maputaland-Pondoland-Albany
Mediterranean Basin
Mesoamerica
Mountains of Southwest China
New Caledonia
New Zealand
North American Coastal Plain
Philippines
Polynesia-Micronesia
Southwest Australia
Succulent Karoo
Sundaland
Tropical Andes
Tumbes-Chocó-Magdalena
Western Ghats and Sri Lanka
Wallacea
Mountains of Central Asia
California Floristic Province
Madrean Pine-Oak Woodlands

## Slide 6
MADAGASCAR AND THE INDIAN OCEAN ISLANDS

## Slide 7: CEPF Work to Date
© Jacques de Spéville - volunteer photographer - Mauritian Wildlife Foundation
Active in the hotspot 2001-2012 and 2016-present
Invested $15 million in grants
>160 projects supported
1.6 M ha of PAs created or expanded
1.6 M ha of production landscapes with improved management
276,142 males and 273,615 females with non-cash benefits
RIT: Fondation Tany Meva

## Slide 8: GCF Program
Accredited Entity: AFD
Executing Entity: CI
Timeline: 10 years (2021-2031)
Total budget: $49.2 million
GCF financing: $38 million grant
Result areas: increased resilience of:
  Most vulnerable people, communities and regions
  Ecosystems and ecosystem services
Pre-concept to effectiveness: 3 years
© Olivier Langrand

## Slide 9
Rationale:
People, agricultural lands and infrastructure are concentrated in coastal zones, which are exposed to sea-level rise and increased frequency and severity of cyclones
Ecosystem-based Adaptation (EbA) encourages conservation, improved management and restoration of ecosystems to provide the essential services that people need to adapt to climate variability
Other than a few pilot projects, financing for EbA is currently insufficient and CSOs are not sufficiently engaged
The Comoros, Madagascar, Mauritius and the Seychelles are extremely vulnerable to climate change
© Conservation International/photo by Sterling Zumbrunn

## Slide 10
© Conservation International/photo by Sterling Zumbrunn

## Slide 11
Goal:
Component 1: Developing strategic plans for EbA in the small island biodiversity hotspot that are well aligned with national climate change strategies
Component 2: Supporting EbA activities through grants to CSOs
Component 3: Ensuring long-term sustainability and replicating success through knowledge products and tools for EbA
Reduce the vulnerability of island populations by securing the critical ecosystem services they need to be resilient to climate change
© Conservation International/photo by Sterling Zumbrunn

## Slide 12
@ Jack Tordoff
Expected results
1.23 M ha of intact coastal ecosystems with strengthened management
0.6 M ha of intact watershed forest ecosystems with strengthened management
4,000 ha of degraded coastal ecosystems restored
2,000 ha of degraded watershed forest ecosystems restored
2,000 ha of climate-resilient agroforestry established
2,000 ha of small island ecosystems with alien invasive species removed

## Slide 13
Expected results
33,000 females and 33,000 males with increased income as a result of ecosystem-based livelihood activities
305,000 females and 305,000 males receiving non-cash benefits as a result of enhanced delivery of ecosystem services
25 CSOs with an institutional capacity score of 80% or more on CEPF’s Civil Society Tracking Tool
US$5 M of capital invested in long-term financing mechanisms (endowment funds, revolving funds, etc.) to support EbA activities beyond the end of the program
© Cristina Mittermeier

## Slide 14
© Conservation International/photo by Sterling Zumbrunn

## Slide 15
© Conservation International/photo by Curan Bonham
Output 1.1 Ecosystem profile updated in the hotspot to identify and prioritize EbA actions by CSOs
© Conservation International/photo by Johnson Rakotoniaina

## Slide 16
© Conservation International/photo by Jeannicq Randrianarisoa
Output 1.2 Long-term Vision for civil society engagement in Ecosystem-based Adaptation developed for the hotspot with participation of government, civil society, donor and private sector actors
Output 1.3 Financing Plan developed for the long-term vision document
Output 1.4 Sector and/or development policy targets set for addressing key drivers of ecosystem service loss in the hotspot
Output 1.5 Strategies for engagement with private sector actors for mainstreaming EbA into business practices of industries driving ecosystem service loss completed for the hotspot

## Slide 17
Output 2.1: Priority EbA activities by CSOs supported through grants
© Olivier Langrand
Restore degraded ecosystems: watershed forests, wetlands, mangroves, coral reefs and seagrass meadows
Strengthen management of intact ecosystems: community fire brigades, community conservation teams, collaborative monitoring of protected area management plans, locally managed marine areas, etc.
Pilot and scale-up EbA techniques: climate-resilience agroforestry, assisted regeneration of denuded watersheds with native species, coral reef restoration with seeding units, etc.
Promote ecosystem-based livelihood activities: sustainable fisheries, nature-based tourism, harvesting natural products, etc.
Local leadership and capacity building: through a regional implementation team

## Slide 18
Output 2.2: EbA action impacts quantified through cutting-edge science
© Conservation International/photo by Andoniaina Rambeloson
Support applied research activities that:
improve understanding of the role of specific ecosystems and test the effectiveness of promising EbA techniques
provide quantification and verification of the impacts of grant portfolio on ecosystem services
This work will be led by partner organizations engaged through competitive calls

## Slide 19
Output 3.1: Models, tools and best practices developed under the Programme are widely available and inform other actors developing and implementing EbA actions globally
© Dahari/Image by Ramoulati Benali
Develop innovative knowledge products documenting models, tools and best practices developed under the Program
Support the replication of successful policy demonstrations
Support the replication of EbA action through innovative partnerships between CSOs and the private sector

## Slide 20
Output 3.2: Ensuring the financial and institutional sustainability of multi-sector programs for EbA, including through enhanced public and private partnerships
© Cristina Mittermeier
Support the creation of long-term implementation structures to serve as a steward for the hotspot’s Long-term Vision
Build organizational and technical capacity of CSOs for EbA in the hotspot
Develop resource mobilization strategies to generate additional revenues for EbA programs in the hotspot
Develop innovative models for private sector finance to support EbA actions by CSOs

## Slide 21
© Olivier Langrand
Project implementation arrangements
Donor Council
AFD CI EU GEF GoJ WB
CEPF Secretariat
(at Conservation International)
Regional Implementation Team
Civil Society Organizations
Local International Academic Community-based
NGOs NGOs Institutions Organizations
Public sector partners
Small Grants
Large
Grants
AFD
GCF Accredited Entity
Global funds
RIT Grant
GCF
NDAs
4 countries
= fund flow
= reporting
= partnership
Working Group
Private sector partners
Program funds

## Slide 22
© Olivier Langrand
Monitoring requirements and major milestones
Environmental and social safeguards
Finance and grants management
AFD and GCF requirements

## Slide 23
© Olivier Langrand
Environmental and social safeguards
Safeguard policy | Triggered by
Environmental and Social Assessment | Activities with potential adverse environmental and social impacts
Labor and Working Conditions | All projects
Resource Efficiency and Pollution Prevention | Activities involving control of invasive alien species
Community Health, Safety and Security | Activities with a risk of adverse impacts on the health, safety and security of local people
Restrictions on Land Use and Involuntary Resettlement | Physical relocation of people [ineligible]; restrictions on access to natural resources
Cultural Heritage | Activities with a risk of adverse impacts on tangible and intangible cultural heritage
Gender Equality | All projects
Stakeholder Engagement | All projects

## Slide 24
© Inga Petelski
Annual workplan
 | 2021 |  |  |  |  |  | 2022 |  |  |  |  | 
 | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun
Component 1: Developing strategic plans for EbA in the small island biodiversity hotspot that are well aligned with national climate change strategies |  |  |  |  |  |  |  |  |  |  |  | 
Output 1.1 Ecosystem Profile updated in the hotspot to identify and prioritise EbA actions by CSOs. |  |  |  |  |  |  |  |  |  |  |  | 
Activity 1.1.1 Identification of important Ecosystem Services and areas for EbA. |  |  |  |  |  |  |  |  |  |  |  | 
Evaluate applications to update the ecosystem profile |  |  |  |  |  |  |  |  |  |  |  | 
Award grant(s) to the selected organization(s) |  |  |  |  |  |  |  |  |  |  |  | 
Hold orientation meeting for ecosystem profiling team |  |  |  |  |  |  |  |  |  |  |  | 
Supervise grant(s) for identification of key ecosystem services and areas for EbA (i.e. KBA+) |  |  |  |  |  |  |  |  |  |  |  | 
Review draft report on ecosystem services and KBA+ inventories and maps |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 25
© Inga Petelski
 | 2021 |  |  |  |  |  | 2022 |  |  |  |  | 
 | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun
Activity 1.1.2 Stakeholder consultation to set priorities for CEPF investment in EbA. |  |  |  |  |  |  |  |  |  |  |  | 
Supervise grant(s) for stakeholder consultations in the four project countries |  |  |  |  |  |  |  |  |  |  |  | 
Participate in national stakeholder consultations |  |  |  |  |  |  |  |  |  |  |  | 
Participate in regional consultation meeting |  |  |  |  |  |  |  |  |  |  |  | 
Review draft consultation reports |  |  |  |  |  |  |  |  |  |  |  | 
Activity 1.1.3 Develop and publish updated Ecosystem Profile for the hotspot. |  |  |  |  |  |  |  |  |  |  |  | 
Supervise preparation of ecosystem profile |  |  |  |  |  |  |  |  |  |  |  | 
Review draft ecosystem profile |  |  |  |  |  |  |  |  |  |  |  | 
Submit ecosystem profile to AFD and GCF Secretariat for review |  |  |  |  |  |  |  |  |  |  |  | 
Present ecosystem profile to CEPF Donor Council for approval |  |  |  |  |  |  |  |  |  |  |  | 
Publish and disseminate ecosystem profile |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 26
© Inga Petelski
 | 2021 |  |  |  |  |  | 2022 |  |  |  |  | 
 | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun
Output 1.4 Sector and/or development policy targets set for addressing key drivers of ecosystem service loss in the hotspot. |  |  |  |  |  |  |  |  |  |  |  | 
Activity 1.4.1 Identify opportunities for CSOs to engage in mainstreaming EbA into government policies |  |  |  |  |  |  |  |  |  |  |  | 
Work with profiling team to identify opportunties for CSOs to engage in mainstreaming EbA into government policies |  |  |  |  |  |  |  |  |  |  |  | 
Output 1.5 Strategies for engagement with private sector actors for mainstreaming EbA into business practices of industries driving ecosystem service loss completed for the hotspot. |  |  |  |  |  |  |  |  |  |  |  | 
Activity 1.5.1 Identify opportunities for private sector partnerships with CSOs to deliver EbA |  |  |  |  |  |  |  |  |  |  |  | 
Work with profiling team to identify opportunties for private sector partnerships with CSOs to deliver EbA |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 27
© Inga Petelski
 | 2021 |  |  |  |  |  | 2022 |  |  |  |  | 
 | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun
Component 2: Supporting EbA activities through grants to CSOs |  |  |  |  |  |  |  |  |  |  |  | 
Output 2.1. Priority EbA activities by CSOs supported in priority areas as defined in the Ecosystem profile. |  |  |  |  |  |  |  |  |  |  |  | 
Activity 2.1.1 Select and contract Regional Implemention Team (RIT) |  |  |  |  |  |  |  |  |  |  |  | 
Prepare RIT Terms of Reference and RfP |  |  |  |  |  |  |  |  |  |  |  | 
Seek AFD’s approval for the selection process for the RIT |  |  |  |  |  |  |  |  |  |  |  | 
Issue RfP |  |  |  |  |  |  |  |  |  |  |  | 
Evaluate applications received based on technical and financial offers |  |  |  |  |  |  |  |  |  |  |  | 
Recommend selected organization/consortium to CEPF Working Group |  |  |  |  |  |  |  |  |  |  |  | 
Request approval of CEPF Donor Council to award RIT grant to selected organization/consortium |  |  |  |  |  |  |  |  |  |  |  | 
Award grant to the selected organization/consortium |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 28
© Inga Petelski
 | 2021 |  |  |  |  |  | 2022 |  |  |  |  | 
 | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun
Activity 2.1.4 Supervision, Monitoring and evaluation of grant portfolio |  |  |  |  |  |  |  |  |  |  |  | 
Prepare portfolio overview for FY21 |  |  |  |  |  |  |  |  |  |  |  | 
Undertake semi-annual supervision mission (in person or remote, depending on travel restrictions) |  |  |  |  |  |  |  |  |  |  |  | 
Project management |  |  |  |  |  |  |  |  |  |  |  | 
Project reporting milestones |  |  |  |  |  |  |  |  |  |  |  | 
Organize inception workshop |  |  |  |  |  |  |  |  |  |  |  | 
Prepare project inception report |  |  |  |  |  |  |  |  |  |  |  | 
Individual consultations with NDAs to understand their expectations about involvement in the project |  |  |  |  |  |  |  |  |  |  |  | 
Prepare and submit Annual Performance Report |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 29
© Inga Petelski
Opportunities for collaboration
Project | Countries | Funder | Focus
Ensuring climate resilient water supplies in the Comoros Islands | Comoros | GCF through UNDP | Policy reforms to strengthen national water governance. Construction of climate-resilient water infrastructure. Integrated watershed management in 32 watersheds.
Sustainable Landscapes in Eastern Madagascar | Madagascar | GCF through CI | Unlocking private investment in sustainable agriculture and low-emission energy through issuance of a green/climate bond.
Building Regional Resilience through Strengthened Meteorological, Hydrological and Climate Services in the Indian Ocean Commission (IOC) Member Countries | Comoros, Madagascar, Mauritius, Seychelles | GCF through AFD | Establishment of an early-warning system for cyclones and other hazards.
Blue Action Fund (BAF): GCF Ecosystem Based Adaptation Programme in the Western Indian Ocean | Madagascar, Mozambique, South Africa, Tanzania | GCF through KfW | Ecosystem-based adaptation for vulnerable coastal populations through sub-projects to NGOs. Protection of coastal ecosystems and rehabilitation of degraded ecosystems.
Transforming Financial Systems for Climate | 17 countries, including Madagascar | GCF through AFD | Provision of loans through local financial institutions to borrowers in sustainable energy, energy efficiency, housing, agriculture, forestry, water, waste, etc.

## Slide 30
© Cristina Mittermeier
Wrap up